## Sheet1
Phase | Task / Sub-Task | Start Date | End Date | Hours
Phase 1 Setup & Literature | 1.1 Literature review: T-KAN, DDE-PINNs, power spectra in machining, KL divergence as physics metric, PySR symbolic regression | May 1, 2026 | May 7, 2026 | 7
| 1.2 Configure Great Lakes HPC pipeline; verify pykan, T-KAN, PySR dependencies | May 1, 2026 | May 7, 2026 | 5
| 1.3 Build ground-truth DDE simulator from Altintas-Budak stability equations | May 8, 2026 | May 14, 2026 | 5
| 1.4 Select 4 representative datasets (damped, high-fn, multi-tooth, noisy) for Phase 3 dev | May 8, 2026 | May 14, 2026 | 3
Phase 2 Power Spectra & KL Divergence | 2.1 Compute power spectral density (PSD) of xtpos and Forcex signals for all 60 clean datasets | May 15, 2026 | May 19, 2026 | 8
| 2.2 Plot stable vs unstable PSD profiles per dataset; identify tooth-pass and chatter frequency peaks | May 15, 2026 | May 21, 2026 | 5
| 2.3 Compute KL divergence between stable and unstable PSD distributions per dataset and per b/blim bin | May 22, 2026 | May 26, 2026 | 7
| 2.4 Validate: confirm KL divergence is significantly higher near b/blim = 1.0; package as stability-aware loss signal for Phase 3 | May 26, 2026 | May 28, 2026 | 5
Phase 3 Core T-KAN-PINN | 3.1 Install and configure T-KAN; build baseline temporal KAN architecture for second-order dynamics | May 22, 2026 | May 28, 2026 | 10
| 3.2 Formulate DDE residual loss with delay-embedded collocation points (data loss + physics residual + BC loss) | May 29, 2026 | Jun 4, 2026 | 12
| 3.3 Residual physics formulation: T-KAN learns only the nonlinear cutting-force and regenerative coupling terms | May 29, 2026 | Jun 4, 2026 | 10
| 3.4 Add stability-aware KL divergence loss term using PSD profiles from Phase 2 | Jun 5, 2026 | Jun 11, 2026 | 8
| 3.5 Implement learnable delay tau (inferred from data, not hardcoded as 60 / (omega * teeth)) | Jun 5, 2026 | Jun 11, 2026 | 10
| 3.6 Train on one stable and one unstable single dataset; verify chatter reproduction in predicted trajectory | Jun 12, 2026 | Jun 18, 2026 | 12
| 3.7 Debug: collocation density, delay initialisation, gradient instabilities, KL loss weight schedule | Jun 12, 2026 | Jun 18, 2026 | 8
Phase 4 Conditional Forward | 4.1 Extend to conditional architecture accepting omega, b, ktc, teeth, fn, damping alongside time-series window | Jun 19, 2026 | Jun 25, 2026 | 15
| 4.2 Train on all 60 clean datasets with leave-dataset-out validation; GroupKFold strategy | Jun 19, 2026 | Jun 28, 2026 | 20
| 4.3 Compare predicted trajectories against held-out files; overlay reconstructed stability lobes vs Altintas-Budak | Jun 29, 2026 | Jul 2, 2026 | 10
Phase 5 Inverse Problem | 5.1 Set up adjoint-based parameter inference pipeline for ktc, fn, damping through trained T-KAN-PINN | Jun 29, 2026 | Jul 5, 2026 | 12
| 5.2 Validate inferred parameters against ground-truth metadata across all 60 datasets; report per-dataset error | Jul 6, 2026 | Jul 9, 2026 | 13
| 5.3 Reconstruct stability lobes from inferred parameters; compare vs Altintas-Budak prediction | Jul 10, 2026 | Jul 12, 2026 | 10
Phase 6 PySR Symbolic Extraction | 6.1 Configure PySR with milling-specific operator library (polynomial, sinusoidal, time-shifted) and BIC parsimony penalty | Jul 13, 2026 | Jul 16, 2026 | 8
| 6.2 Run PySR on T-KAN edge activation functions across all conditioning regimes | Jul 13, 2026 | Jul 20, 2026 | 14
| 6.3 Search extracted expressions for regenerative term x(t) - x(t - tau) without explicit hardcoding | Jul 21, 2026 | Jul 24, 2026 | 8
| 6.4 Compute R² between extracted expressions and validated DDE structure; compare against E-SINDy baseline | Jul 24, 2026 | Jul 26, 2026 | 5
Phase 7 Noise Robustness | 7.1 Fine-tune on 1% noise datasets 61-90 starting from clean pretrained T-KAN-PINN checkpoint | Jul 27, 2026 | Jul 30, 2026 | 9
| 7.2 Fine-tune on 5% noise datasets 91-120 | Jul 31, 2026 | Aug 2, 2026 | 8
| 7.3 Report trajectory accuracy, parameter error, PySR fidelity, and KL discrimination at 0%, 1%, 5% noise | Aug 2, 2026 | Aug 2, 2026 | 8
Phase 8 Ablations & XAI | 8.1 Ablation matrix: T-KAN vs MLP, KL loss on/off, residual physics on/off, learnable vs hardcoded delay | Aug 3, 2026 | Aug 7, 2026 | 10
| 8.2 DiCE counterfactuals on T-KAN-PINN inputs (omega, b) for 10+ unstable operating points | Aug 5, 2026 | Aug 8, 2026 | 9
| 8.3 Monte Carlo drift: perturb fn ±5%, ktc ±10%, damping ±15% (N=500); report survival rates | Aug 8, 2026 | Aug 9, 2026 | 6
Phase 9 Writeup | 9.1 Draft technical report: intro, method, results, ablations, discussion, future work | Aug 10, 2026 | Aug 13, 2026 | 12
| 9.2 NeurIPS ML4PS workshop paper draft (4-page format) | Aug 13, 2026 | Aug 15, 2026 | 5
| 9.3 Review with Prof. Abell, incorporate feedback, finalise and submit technical report | Aug 15, 2026 | Aug 15, 2026 | 3
Total Estimated Hours |  |  |  | 300